## issues
Epic 1
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 1](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/1) | USER STORY : Set up GiHub repository | As a Developer, I need to set-up a repository on GitHub platform to be able to have control over versions of project. | Working GitHub repository. | Not Applicable | N/A | PASS
[# 2](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/2) | USER STORY : Create working Django app | As a Developer, I need to install all dependencies, correctly set settings.py and create working app in local environment. | All dependencies are installed, settings.py all set for local view and when project is ran locally, symbol of correctly set app is shown (rocket). | Not Applicable | [251e391](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/b606c30f5658763d01e6535726f4a4d92d4ce0e0) | PASS
[# 3](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/3) | USER STORY : Deploy to Heroku | As a Developer I need to create a working Heroku deployement. | Working Heroku Deployment, when first deployed site accesed, it gives hint of correctly installed Django App (DEBUG = True). Create if statement in settings.py for DEBUG = False when deployed. | Not Applicable | [cca2ec2](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/cca2ec26e07aaf9676052fa4a2db3a2be50f366a) | PASS
Epic 2
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 13](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/13) | USER STORY : Define Database Schema and create sub apps. | As a Developer, I need to create databse schema that fits the purpose of the project and also create all the modular apps that will be used in the project. | All Django apps are created and database schema in place to stick to. | ( Appendix 68 ) | [1202424](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/12024248cc53b3966b70377388984862bfc50c0b) | PASS
[# 14](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/14) | USER STORY : Create database realtionships | As a Developer, I need to define relatinships between models and import the relationships into working apps models. | All models are working with the relationships defined, all models that are related to other app models are linked via import statements. | ( Appendix 69 ) | [1202424](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/12024248cc53b3966b70377388984862bfc50c0b) | PASS
[# 15](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/15) | USER STORY : Implement Data Validation in Models | As a Developer, I need implement data validation rules within Glimmer database models. | All values insrted to database are the correct values and types, all applicable fileds are all set to be required or/and to be unique or/and nullable/not nullable. | ( Appendix 70 ) | [1202424](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/12024248cc53b3966b70377388984862bfc50c0b) | PASS
Epic 3
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 17](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/17) | USER STORY : Implement user registration | As a Site User I am able to register to create new account and to select username and passsword. | Not registered user : When I visit the site then I am able to register, select free username and create valid password. | ( Appendix 71 ) | [1ceb3cf](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/1ceb3cfbc0d845f7fc77cbbe23e657f34159fe16) | PASS
[# 18](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/18) | USER STORY : Log In | As a Site User I am able to Log In to see registered user section. | 1.Registered user : When I visit the site then I am able to login via login link. 2.Not registered user : When I visit the site and trying to log in then I am given error message that user does not exist. | ( Appendix 72 ) and ( Appendix 73 ) | [1ceb3cf](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/1ceb3cfbc0d845f7fc77cbbe23e657f34159fe16) | PASS
[# 19](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/19) | USER-STORY : Reset my password if forgotten | As a Site User I am able to Reset My Password to change my password if forgotten. | When I visit login page then I have the option to reset my password via provided link and email with reset link is sent to me. | ( Appendix 74 ) | [491242a](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/491242a472f186f75c15335507cfe605ef1d5dbd) | PASS
[# 48](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/48) | USER STORY : Log out | As a Site User, I am able to log out to leave the site functions for registered users. | 1.Registered user : When I am logged in then I am able to logout. 2.Not registered user : Don't have that option. | ( Appendix 75 ) | [491242a](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/491242a472f186f75c15335507cfe605ef1d5dbd) | PASS
Epic 4
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 21](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/21) | USER STORY : Opt In/Out for Newsletter | As a Site User I can Opt In/Out for Newsletter to be able to change my preferences. | 1.Logged in user : When I navigate to "My Details" section then I can mark/unmark to receive marketing emails. 1.Not logged in user : Don't have that option as not logged in. | ( Appendix 76 ) | [1f168ee](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/1f168eeb43330c02cb3ad79931c84002e46a5ede) | PASS
[# 22](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/22) | USER STORY : Change Details (Phone Nuber, Email Address, etc.) | As a Site User I can Update My Detail to be able to manage my account in case of changes. | 1. Logged in user : When I login then I can clearly navigate to "My Details" section where I can change my details. 2. Not logged in user : Don't have that option as not logged in. | ( Appendix 76 ) | [1f168ee](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/1f168eeb43330c02cb3ad79931c84002e46a5ede) | PASS
[# 23](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/23) | USER STORY : Delete my account | As a Site User I can Delete My Account to be able to opt out from all services. | 1. Logged in user : When I navigate to "my details" then I have the option of delete my account entirely.2. Not logged in user : Don't have that option as not logged in. | ( Appendix 76 ) and ( Appendix 77 ) | [1f168ee](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/1f168eeb43330c02cb3ad79931c84002e46a5ede) | PASS
Epic 5
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 25](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/25) | USER STORY : See News Highlights on landing page | As a Site User I can See the News Highlights to see three newest news posts. | When I visit the site's landing page then I am able to see news highlights on a carousel rotation. | ( Appendix 78 ) | [503f6ab](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/503f6ab884226ae2453e5598ae5792f19e83788d) | PASS
[# 26](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/26) | USER STORY : See list of all News & Details | As a Site User I can Visit Page with all News to be able tosee all News. | When I visit the site's landing page then I am comfortably able to navigate to list of all news and see details of each news posts. | ( Appendix 79 ) and ( Appendix 80 ) | [503f6ab](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/503f6ab884226ae2453e5598ae5792f19e83788d) | PASS
[# 27](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/27) | USER STORY : Like/Unlike News | As a Site User I can Like or Unlike News Post to highlight the News Post as interesting. | Logged in user : When I open news post detail then I am able to like or unlike the post. Not logged in user : Doesn't have that option. | ( Appendix 81 ) | [11010d4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/11010d40fbe33d667ee6804c4869e5ae96aeeb7c) | PASS
[# 28](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/28) | USER STORY : Comment on News | As a Site User I can Comment on News Post to share my opinion. | Logged in user : When I open news post detail then I am able to add comment on the relevant news post. Not logged in user : Doesn't have that option. | ( Appendix 82 ) | [a42b417](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/a42b4178dacdd64c00b0bbb532e20f1fe75ab06f) | PASS
[# 29](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/29) | USER STORY : See other users Comments | As a Site User I can see other comments on News Posts to read other Users opinions. | Logged in user :When I open news post detail then I am able to see other people comments.Not logged in user :Doesn't have that option. | ( Appendix 82 ) | [a823dfc](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/a823dfc321ea432c1fe688e19e6739187d252c0a) | PASS
[# 30](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/30) | USER STORY : See who else liked | As a Site User I can see who else liked News Posts to see who else has the same opinion. | Logged in user :When I open news post detail then I am able to see who else liked the post.Not logged in user :Doesn't have that option. | ( Appendix 83 ) | [7b09a2e](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/7b09a2ec75cffb8656d34d00b1f34a49b5374161) | PASS
Epic 6
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 32](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/32) | USER STORY : List of Styles | As a Site User I can See list of available styles to be able to choose one to see details. | When I navigate to styles from navbar then I see list of all styles that are available. | ( Appendix 84 ) and ( Appendix 85 ) | [f989ca8](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/f989ca83477ccde96828399d58d3fffe0a949450) | PASS
[# 33](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/33) | USER STORY : Styles Details | As a Site User I can See Style details to see description and what artist does this particular style. | When I open list of styles then I like to be able to see all details about the particular style including likes and "tries". | ( Appendix 85 ) | [9e5415a](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/9e5415a8102cb5d27f315315407267ae87e3cbc4) | PASS
[# 34](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/34) | USER STORY : Like / Unlike Styles | As a Site User I can Like / Unlike particular Style to express my opinion. | Logged in user : When I open detail of a particular style then I am able to like/unlike style.Not logged in user : Doesn't have that option. | ( Appendix 85 ) | [b22d266](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/b22d266264181a63874720aa066c9c87c3ff4b1b) | PASS
[# 35](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/35) | USER STORY : See who else likes the particular Style | As a Site User I can see who else liked the particular style to see who else has same opinion. | Logged in user :When I open style detail then I am able to see who else liked the style.Not logged in user :Doesn't have that option. | ( Appendix 83 ) | [9e5415a](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/9e5415a8102cb5d27f315315407267ae87e3cbc4) | PASS
[# 36](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/36) | USER STORY : Mark / Unmark Styles as "Wan't to try" | As a Site User I can Mark / Unmark particular style to express my interest. | Logged in user :When I open detail of a particular style then I am able to mark it as "try/untry".Not logged in user :Doesn't have that option. | ( Appendix 85 ) | [b22d266](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/b22d266264181a63874720aa066c9c87c3ff4b1b) | PASS
[# 37](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/37) | USER STORY : See who else marked the partucular style as "Want to try" | As a Site User I can see who else marked partulcar style as "Want to try to see who else has same interests. | Logged in user :When I open style detail then I am able to see who else marked the style as "want to try".Not logged in user :Doesn't have that option. | ( Appendix 86 ) | [9e5415a](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/9e5415a8102cb5d27f315315407267ae87e3cbc4) | PASS
Epic 7
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 39](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/39) | USER STORY : Create a booking | As a Site User I can Create new booking and to be able to choose date, time and artist. | Logged in user :When I navigate to "my bookings" then I am able to create a booking.Not logged in user :Doesn't have that option. | ( Appendix 87 ) | [a817445](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/a817445b3fd1c8c5fc891bcee4b777a1f83972a4) | PASS
[# 40](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/40) | USER STORY : See my bookings | As a Site User I can See all my bookings to be able to keep record of them. | Logged in user :When I navigate to "My bookings", I can clearly see upcoming and past bookings.Not logged in user :Doesn't have that option. | ( Appendix 88 ) | [0893feb](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/0893feb43f831438ef9f3503e409d8f4c9d49c7b) | PASS
[# 41](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/41) | USER STORY : Update my bookings | As a Site User I can Update any of my future bookings to change details. | Logged in user :When I navigate to "My Bookings" then I am able to select a booking that I wan to change.Not logged in user :Doesn't have that option. | ( Appendix 89 ) | [1ab529e](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/1ab529e66fe125bfab99fe14c65e45a7f758af10) | PASS
[# 42](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/42) | USER STORY : Delete my bookings | As a Site User I can Delete any of my future bookings to cancel the booking. | Logged in user :When I navigate to my bookings then I can cancel the booking(s).Not logged in user :Doesn't have that option. | ( Appendix 89 ) | [74d849c](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/74d849cdd3887da3019f13dc34ee4799ed6ef771) | PASS
[# 43](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/43) | USER STORY : Leave review after booking finished | As a Site User I can leave review to let the others know about my satisfaction. | Logged in user :When my booking is done I can navigate to "My bookings" and leave a review for particular booking.Not logged in user :Doesn't have that option. | ( Appendix 90 ) | [0ff4da1](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/0ff4da14bc3eecb6ab818efe9883789a81cf3a26) | PASS
[# 44](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/44) | USER STORY : Get confirmation of my booking being approved | As a Site User I get confirmation email when my booking is approved to be sure the booking is going ahead. | When I my booking is confirmed by Site Admin then I am notified via email. | ( Appendix 91 ) | [8e4ef41](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/8e4ef412be0228a064f9bc9d698b4c8fc402f14c) | PASS
Epic 8
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 52](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/52) | USER STORY : Create search bar on landing page | As a Site User I am able to use search function through Artists, Styles and News to quickly find what am I looking for. | When I open the landing page then I can see the search bar. | ( Appendix 78 ) | [0c9cebe](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/0c9cebea491867384d9fc385f5f1e34935bba0ce) | PASS
[# 53](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/53) | USER STORY : Provide search results | As a Site User I can see search result to easily navigate through them. | When I submit search criteria and clcik the search button then I am able to see the results. | ( Appendix 92 ) | [3a4d8f3](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3a4d8f3311e5117b90a6619f1d2efe8b7e60e39b) | PASS
Epic 9
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 55](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/55) | USER STORY : Delete user | As a Site Admin, I can delete user accounts that are no longer in use to make sure my database of clients is up to date. | When I log in to admin suite then I can navigate to user profiles and delte user entirely. | ( Appendix 93 ) | [3bf93b4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3bf93b4f0ab84850a9181d9d96973adcbd8a7b66) | PASS
[# 56](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/56) | USER STORY : Manage news | As a Site Admin, I can add news posts to keep content up to date. | When I log in to admin suite then I can navigate to News and add, change or delete news content. | ( Appendix 94 ) | [3bf93b4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3bf93b4f0ab84850a9181d9d96973adcbd8a7b66) | PASS
[# 57](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/57) | USER STORY : Manage available styles | As a Site Admin, I can add available styles to keep content up to date. | When I log in to admin suite then I can navigate to Styles and add, change or delete available styles. | ( Appendix 95 ) | [3bf93b4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3bf93b4f0ab84850a9181d9d96973adcbd8a7b66) | PASS
[# 58](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/58) | USER STORY : Manage artists | As a Site Admin, I can add nail artists to keep list of employees up to date. | When I log in to admin suite then I can navigate to Artists and, change and delete avalable artists. | ( Appendix 96 ) | [3bf93b4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3bf93b4f0ab84850a9181d9d96973adcbd8a7b66) | PASS
[# 59](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/59) | USER STORY : Approve comments | As a Site Admin, I can approve comments to ensure no harmful content. | When I log in to admin suite then I can navigate to Comments and approve or delete comments. | ( Appendix 97 ) | [3bf93b4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3bf93b4f0ab84850a9181d9d96973adcbd8a7b66) | PASS
[# 60](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/60) | USER STORY : Mark bookings as confirmed | As a Site Admin, I can mark bookings as confirmed to inform user of the progress. | When I log in to admin suite then I can navigate to Bookings and mark pending bookings as confirmed. | ( Appendix 98 ) | [3bf93b4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3bf93b4f0ab84850a9181d9d96973adcbd8a7b66) | PASS
[# 61](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/61) | USER STORY : Mark bookings as done | As a Site Admin, I can mark bookings as done to inform user of the progress and allow user to rate. | When I log in to admin suite then I can navigate to Bookings and mark pending bookings as done. | ( Appendix 99 ) | [3bf93b4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3bf93b4f0ab84850a9181d9d96973adcbd8a7b66) | PASS
[# 62](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/62) | USER STORY : Last-minute bookings | As a Site Admin, I need to provide users with "last-minute" bookings available to let them know how many slots are free the following day. | Logged in user :When Site Users log in and navigate to "My Bookings" then they are provided with info of the following day free slots.Not logged in user :Doesn't have that option. | ( Appendix 100 ) | [7bb09fb](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/7bb09fb6b273ce873b23350cf89df2387bb26d62) | PASS
Epic 10
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 71](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/71) | USER STORY : Intuitive navigation | As a Site Developer, I need to insure easy navigation throughout the site. | Not Applicable | [Please see readme.md](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/blob/main/README.md) | Not Applicable | PASS
[# 72](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/72) | USER STORY : Color scheme | As a Site Developer, I need to insure same color scheme throughout the site | Not Applicable | [Please see readme.md](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/blob/main/README.md) | Not Applicable | PASS
[# 73](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/73) | USER STORY : WAVE compatibility | As a Site Developer, I need to insure that site can be easily navigated using page readers, so it doen't have WAVE issues. | Not Applicable | [Please see readme.md](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/blob/main/README.md) | Not Applicable | PASS
PASS
Epic 11
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 75](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/75) | USER STORY : W3C HTML validation | As a Site Developer, I need to ensure *.html files do pass the W3C validation. | Not Applicable | [Please see readme.md](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/blob/main/README.md) | Not Applicable | PASS
[# 76](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/76) | USER STORY : W3C CSS validation | As a Site Developer, I need to ensure style.css file do pass the W3C validation. | Not Applicable | [Please see readme.md](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/blob/main/README.md) | Not Applicable | PASS
[# 77](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/77) | USER STORY : JS validation | As a Site Developer, I need to ensure *.js files do pass the JS Lint validation. | Not Applicable | [Please see readme.md](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/blob/main/README.md) | Not Applicable | PASS
[# 78](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/78) | USER STORY : PEP8 validation | As a Site Developer, I need to ensure *.py file do pass the PEP8 validation. | Not Applicable | [Please see readme.md](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/blob/main/README.md) | Not Applicable | PASS
Epic 12
Issue | Title | User Story | Acceptance Criteria | Implementation | Final Commit | Result
[# 80](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/80) | USER STORY : Admin interface that copies functions of Django Admin Suite | As a Site Developer I need to come up with cusom admin interface that ensures all functions of Django Admin Suite, | When I log in as Admin and click Admin in NavBar then I am able to use same functions as logging in to Django Admin Suite. | Not implemented, left in the back log. Marked as WONT'T HAVE on Kanban Board | Not Applicable | FAIL

## py
Directory | File | Result
administrator | `admin.py` | <span style="color:green;">PASS</span>
administrator | `urls.py` | <span style="color:green;">PASS</span>
administrator | `views.py` | <span style="color:green;">PASS</span>
artists | `admin.py` | <span style="color:green;">PASS</span>
artists | `models.py` | <span style="color:green;">PASS</span>
artists | `urls.py` | <span style="color:green;">PASS</span>
artists | `views.py` | <span style="color:green;">PASS</span>
bookings | `admin.py` | <span style="color:green;">PASS</span>
bookings | `forms.py` | <span style="color:green;">PASS</span>
bookings | `models.py` | <span style="color:green;">PASS</span>
bookings | `urls.py` | <span style="color:green;">PASS</span>
bookings | `views.py` | <span style="color:green;">PASS</span>
landing | `admin.py` | <span style="color:green;">PASS</span>
landing | `forms.py` | <span style="color:green;">PASS</span>
landing | `urls.py` | <span style="color:green;">PASS</span>
landing | `views.py` | <span style="color:green;">PASS</span>
news | `admin.py` | <span style="color:green;">PASS</span>
news | `forms.py` | <span style="color:green;">PASS</span>
news | `models.py` | <span style="color:green;">PASS</span>
news | `urls.py` | <span style="color:green;">PASS</span>
news | `views.py` | <span style="color:green;">PASS</span>
profilemanager | `admin.py` | <span style="color:green;">PASS</span>
profilemanager | `forms.py` | <span style="color:green;">PASS</span>
profilemanager | `models.py` | <span style="color:green;">PASS</span>
profilemanager | `urls.py` | <span style="color:green;">PASS</span>
profilemanager | `views.py` | <span style="color:green;">PASS</span>
styles | `admin.py` | <span style="color:green;">PASS</span>
styles | `forms.py` | <span style="color:green;">PASS</span>
styles | `models.py` | <span style="color:green;">PASS</span>
styles | `urls.py` | <span style="color:green;">PASS</span>
styles | `views.py` | <span style="color:green;">PASS</span>
glimmer | `asgi.py` | <span style="color:green;">PASS</span>
glimmer | `settings.py` | <span style="color:red;">FAIL</span> *( Appendix 53 )*
glimmer | `urls.py` | <span style="color:green;">PASS</span>
glimmer | `wsgi.py` | <span style="color:green;">PASS</span>

## html
Directory | File | State | Result
administrator | `admin_menu.html` | Only Logged in as admin | <span style="color:green;">PASS</span>
artists | `artist_detail.html` | Not Applicable | <span style="color:green;">PASS</span>
artists | `artists.html` | Not Applicable | <span style="color:green;">PASS</span>
bookings | `booking_cancel_confirm.html` | Only Logged in | <span style="color:green;">PASS</span>
bookings | `bookings.html` | Only Logged in | <span style="color:green;">PASS</span>
bookings | `edit_booking.html` | Only Logged in | <span style="color:green;">PASS</span>
bookings | `new_booking.html` | Only Logged in | <span style="color:green;">PASS</span>
landing | `index.html` | Not Applicable | <span style="color:green;">PASS</span>
landing | `search_results.html` | Not Applicable | <span style="color:green;">PASS</span>
news | `all_news.html` | Not Applicable | <span style="color:red;">FAIL 1000 + errors</span> *( Appendix 54 )*
news | `news_detail.html` | Logged In | <span style="color:red;">FAIL 400 + errors</span> *( Appendix 54 )*
news | `news_detail.html` | Logged Out | <span style="color:red;">FAIL 400 + errors</span> *( Appendix 54 )*
profilemanager | `my_details.html` | Only Logged In | <span style="color:green;">PASS</span>
styles | `style_detail.html` | Logged In | <span style="color:green;">PASS</span>
styles | `style_detail.html` | Logged Out | <span style="color:green;">PASS</span>
styles | `styles.html` | Not Applicable | <span style="color:green;">PASS</span>
templates | `403.html` | Not Applicable | <span style="color:green;">PASS</span>
templates | `404.html` | Not Applicable | <span style="color:green;">PASS</span>
templates | `500.html` | Not Applicable | <span style="color:green;">PASS</span>
templates | `base.html` | Not Applicable | <span style="color:green;">PASS</span>
templates | `footer.html` | Not Applicable | <span style="color:green;">PASS</span>
templates | `header.html` | Logged In | <span style="color:green;">PASS</span>
templates | `header.html` | Logged Out | <span style="color:green;">PASS</span>
account | `*.html` | Logged In | <span style="color:green;">PASS</span>
account | `*.html` | Logged Out | <span style="color:green;">PASS</span>

## js
File | Result
`comments_news.js` | <span style="color:green;">PASS</span>
`comments_styles.js` | <span style="color:green;">PASS</span>
`edit_booking.js` | <span style="color:green;">PASS</span>
`messages.js` | <span style="color:green;">PASS</span>
`new_booking.js` | <span style="color:green;">PASS</span>

## wave
Directory | File | State | Errors | Alerts | Nature of problem | Result
administrator | `admin_menu.html` | Only Logged in as admin | No | Yes | Redundant links | <span style="color:green;">PASS</span>
artists | `artist_detail.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
artists | `artists.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
bookings | `booking_cancel_confirm.html` | Only Logged in | No | Yes | Redundant links | <span style="color:green;">PASS</span>
bookings | `bookings.html` | Only Logged in | No | Yes | Redundant links | <span style="color:green;">PASS</span>
bookings | `edit_booking.html` | Only Logged in | No | Yes | Redundant links | <span style="color:green;">PASS</span>
bookings | `new_booking.html` | Only Logged in | No | Yes | Redundant links | <span style="color:green;">PASS</span>
landing | `index.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
landing | `search_results.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
news | `all_news.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
news | `news_detail.html` | Logged In | No | Yes | Redundant links | <span style="color:green;">PASS</span>
news | `news_detail.html` | Logged Out | No | Yes | Redundant links | <span style="color:green;">PASS</span>
profilemanager | `my_details.html` | Only Logged In | No | Yes | Redundant links | <span style="color:green;">PASS</span>
styles | `style_detail.html` | Logged In | No | Yes | Redundant links | <span style="color:green;">PASS</span>
styles | `style_detail.html` | Logged Out | No | Yes | Redundant links | <span style="color:green;">PASS</span>
styles | `styles.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
templates | `403.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
templates | `404.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
templates | `500.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
templates | `base.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
templates | `footer.html` | Not Applicable | No | Yes | Redundant links | <span style="color:green;">PASS</span>
templates | `header.html` | Logged In | No | Yes | Redundant links | <span style="color:green;">PASS</span>
templates | `header.html` | Logged Out | No | Yes | Redundant links | <span style="color:green;">PASS</span>
account | `*.html` | Logged In | No | Yes | Redundant links | <span style="color:green;">PASS</span>
account | `*.html` | Logged Out | No | Yes | Redundant links | <span style="color:green;">PASS</span>

## bugs
Bugs
Issue | Title | Description | Screenshot | Solution | Final Commit | Result
[# 45](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/45) | BUG : Nav-bar isnt' clickable when scrolled down | The Nav-bar stops being clickable after scrolled down the page. | Not Available | Z-index of header changed to 9 | [3020bfc](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/3020bfc1b88cba55d19d672acf1999e3c4212853) | FIXED
[# 47](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/47) | BUG : Styles "want to try" not displaying correct amount of "want to try" marks | Styles "want to try" not displaying correct amount of "want to try" marks. | Not Available | List sorted by number of "want to try" but displaying number of "likes" originally. After patch, list sorted by number of "want to try" and displays number of "want to try". | [ec56b3c](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/ec56b3c3455d1634cfcd5e3e93e97221ecbd4007) | FIXED
[# 46](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/46) | BUG : List of News doesn't filter "published" or "not published" news | List of news doesn't filter published or not published news. | Not Available | `.filter(is_published=1)` added as a search query. | [503f6ab](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/503f6ab884226ae2453e5598ae5792f19e83788d) | FIXED
[# 50](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/50) | BUG : Artist rating not displaying properly when 4.75 | The rating of artists goes to error when rating is 4.75. | *( Appendix 63 )* | Add equal ` >=` to if else statement on landing page. | [bd08ac1](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/bd08ac1392d556365fc42a2aa7a699ecb7f17d79) | FIXED
[# 49](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/49) | BUG : URL's doubleng | All URL's are doubling after making project more modular into smaller apps. | Not Available | Wrong setup of project + apps URL's, all fixed. | [fe0b058](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/fe0b058e78c136c73dce7ca2a0b7d272054d225f) | FIXED
[# 63](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/63) | BUG : Sizing of forms background | Forms field are overfloving (x axle) from background container. | *( Appendix 64 )* | `@media screen and (max-width: 991px) { .form-background { width: 80%; } }` added to style.css | [d71d7f3](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/d71d7f3d9bced7c66dd36ed8b7ccb2874d24fa0f) | FIXED
[# 68](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/68) | BUG : "Last minute" shows negative numbers | Last minute section shows negative numbers of bookings between midnight and 9am. | *( Appendix 65 )* | Bug fixed with extending if statement to start counting free slots at midnight by adding `if ( time_now >= datetime.strptime("00:00", "%H:%M").time() and time_now < datetime.strptime("09:00", "%H:%M").time() ): slots_left_today = 8` | [b0d9f79](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/b0d9f799e689f525461e6eb541d3c87d18bd5a05) | FIXED
[# 69](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/69) | BUG : Comments link scrolls to top of page | Both, Styles and News scroll to top of the page when "Show comments" link is clicked. | Not Available | `event.preventDefault();` added to both js scripts to prevent scrolling. | [e299eec](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/e299eec55ed063aa426a6d2bf5ad59ba3cd3cf0c) | FIXED
[# 64](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/64) | BUG : Menu not displaying correctly | Menu after clicking the burger icon isn't displaying correctly. | *( Appendix 66 )* | Adjust CSS styling via media queries | [f8925bb](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/f8925bbc5264f77e3b411a29b952a083d89bad65) | FIXED
[# 65](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/65) | BUG : Length of menu items | Nav-bar items overflow over logo. | *( Appendix 67 )* | Adjust CSS styling via media queries | [f8925bb](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/f8925bbc5264f77e3b411a29b952a083d89bad65) | FIXED
[# 66](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/66) | BUG : Creating new booking throws "Naive time warning" | When creating new booking, termial displays warning about naive time being used. | *( Appendix 68 )* | `timezone.make_aware(new_booking.date_time)` - added to new booking | [160c5d4](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/160c5d46a89e6e9a99bb913e0bd98d3349551a2c) | FIXED
[# 67](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/issues/67) | BUG : "Naive time warning" when editing booking | When editing existing booking, terminal displays warning about naive time being used. | *( Appendix 69 )* | `timezone.make_aware(new_booking.date_time)` - added to edited booking | [275b529](https://github.com/tomik-z-cech/PP4-Aneta-s-Glimmer/commit/275b529fddcd0725a5c9746f6f76c4d20f08311e) | FIXED

## Test Cases
PP4 - Aneta's Glimmer
Test Case 001 - General Site Navigation - Not registered user
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on News | News List Displayed | Worked as expected | PASS
3 | Click on News Link | News Detail Displayed | Worked as expected | PASS
4 | Click on Styles | Styles List Displayed | Worked as expected | PASS
5 | Click on Style Link | Style Detail Displayed | Worked as expected | PASS
6 | Click on Team | Team Members List Displayed | Worked as expected | PASS
7 | Click on Team member Link | Team Member Details Displayed | Worked as expected | PASS
8 | Click on Logo | Landing Page Displayed | Worked as expected | PASS
9 | Click on Home | Landing Page Displayed | Worked as expected | PASS
10 | Click on Register | Register Form Displayed | Worked as expected | PASS
11 | Click Terms and Conditions Link | Modal with T&C's Displayed | Worked as expected | PASS
12 | Click Back button on Modal | Modal Closes | Worked as expected | PASS
PP4 - Aneta's Glimmer
Test Case 002 - Search Function
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click Search | Error message "empty field" Displayed | Worked as expected | PASS
3 | Fill In Search Term and click Search | Search Results Displayed | Worked as expected | PASS
4 | Click on link in Artists Results | Team Member Detail Displayed | Worked as expected | PASS
5 | Return Back to Home Page | Landing Page Displayed | Worked as expected | PASS
6 | Fill In Search Term and click Search | Search Results Displayed | Worked as expected | PASS
7 | Click on link in News Results | News Detail Displayed | Worked as expected | PASS
8 | Return Back to Home Page | Landing Page Displayed | Worked as expected | PASS
9 | Fill In Search Term and click Search | Search Results Displayed | Worked as expected | PASS
10 | Click on link in Styles Results | Style Detail Displayed | Worked as expected | PASS
PP4 - Aneta's Glimmer
Test Case 003 - Registering new user
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Register | Register Form Displayed | Worked as expected | PASS
3 | Click on Register button | Error message "missing fields" Displayed | Worked as expected | PASS
4 | Click on Register | Register Form Displayed | Worked as expected | PASS
5 | Click Terms and Conditions Link | Modal with T&C's Displayed | Worked as expected | PASS
6 | Click Back button on Modal | Modal Closes | Worked as expected | PASS
7 | Fill in username "tomas" | Error message "existing user" Displayed | Worked as expected | PASS
8 | Fill in email "tkubancik@gmail.com" | Error message "existing user" Displayed | Worked as expected | PASS
9 | Correctly fill in user detials | Info about validation email sent displayed | Worked as expected | PASS
10 | Open your email provider and click the validating link | Confirmation form displayed | Worked as expected | PASS
11 | Click "Confirm" button | Login Page displayed | Worked as expected | PASS
PP4 - Aneta's Glimmer
Test Case 004 - Changing user's name, phone number, marketing preferences
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Login | Login form displayed | Worked as expected | PASS
3 | Provide correct credentials and click login button | My Bookings Page displayed | Worked as expected | PASS
4 | Click on My Profile | Prepopulated My Profile Form displayed | Worked as expected | PASS
5 | Change details in input fields | None | Worked as expected | PASS
6 | Click "Save Changes" button | Landing page displayed with message | Worked as expected | PASS
PP4 - Aneta's Glimmer
Test Case 005 - Changing user's email
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Login | Login form displayed | Worked as expected | PASS
3 | Provide correct credentials and click login button | My Bookings Page displayed | Worked as expected | PASS
4 | Click on My Profile | Prepopulated My Profile Form displayed | Worked as expected | PASS
5 | Click on "Change Email" button | Email change form displayed | Worked as expected | PASS
6 | Don't provide any email | None | Worked as expected | PASS
7 | Click on "Add email" button | Error message "empty field" Displayed | Worked as expected | PASS
8 | Provide new email address | None | Worked as expected | PASS
9 | Click on "Add email" button | Provided email address appears in list as unverified | Worked as expected | PASS
Message displayed + verification email sent
10 | Select newly provided email address | None | Worked as expected | PASS
11 | Click on "Re-Send Verification" | Message displayed + verification email sent | Worked as expected | PASS
12 | Select newly provided email address | None | Worked as expected | PASS
13 | Click on "Remove" | Message displayed + email removed from list | Worked as expected | PASS
PP4 - Aneta's Glimmer
Test Case 006 - Changing user password
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Login | Login form displayed | Worked as expected | PASS
3 | Provide correct credentials and click login button | My Bookings Page displayed | Worked as expected | PASS
4 | Click on My Profile | Prepopulated My Profile Form displayed | Worked as expected | PASS
5 | Click on "Change Password" button | Password change form displayed | Worked as expected | PASS
6 | Don't provide any information | None | Worked as expected | PASS
7 | Click on "Change Password" button | Error message "empty field" Displayed | Worked as expected | PASS
8 | Provide old & new passwords (different) | None | Worked as expected | PASS
9 | Click on "Change Password" button | Error message "provide same passwrods" Displayed | Worked as expected | PASS
10 | Provide old & new passwords (same) | None | Worked as expected | PASS
11 | Click on "Change Password" button | Confirmation Message displayed | Worked as expected | PASS
PP4 - Aneta's Glimmer
Test Case 007 - Bookings CRUD
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Login | Login form displayed | Worked as expected | PASS
3 | Provide correct credentials and click login button | My Bookings Page displayed | Worked as expected | PASS
4 | Click on "New Booking" button | New booking form displayed | Worked as expected | PASS
5 | Select Booked style | Booked Artist Field Appears | Worked as expected | PASS
6 | Select Booked Artist | Date field appears | Worked as expected | PASS
7 | Change booked style | Date field disappears | Worked as expected | PASS
Selection of artists modifies based on style
8 | Change booked date | Booked Time field appears | Worked as expected | PASS
9 | Change booked artist | Booked time field disappears | Worked as expected | PASS
10 | Change booked date | Booked Time field appears | Worked as expected | PASS
11 | Change booked time | "Create booking" button appears | Worked as expected | PASS
12 | Click on "Create booking" button | My Bookings Page displayed | Worked as expected | PASS
Email sent + message displayed
13 | Select Pending bookings | Pending bookings displayes with newly created booking | Worked as expected | PASS
14 | Click on "Edit" button | Prepopulated booking form displayed | Worked as expected | PASS
15 | Change booked style | Date field disappears | Worked as expected | PASS
|  | Selection of artists modifies based on style | Worked as expected | PASS
16 | Change booked date | Booked Time field appears | Worked as expected | PASS
17 | Change booked artist | Booked time field disappears | Worked as expected | PASS
18 | Change booked date | Booked Time field appears | Worked as expected | PASS
19 | Change booked time | "Change booking" button appears | Worked as expected | PASS
20 | Click on "Change booking" button | My Bookings Page displayed | Worked as expected | PASS
Email sent + message displayed
21 | Select Pending bookings | Pending bookings displayes with newly created booking | Worked as expected | PASS
22 | Click on "Cancel" button | Cancel form displayed | Worked as expected | PASS
23 | Click "No, take me back" button | My Bookings Page displayed | Worked as expected | PASS
24 | Click on "Cancel" button | Cancel form displayed | Worked as expected | PASS
25 | Click "Yes, cancel" button | My Bookings Page displayed | Worked as expected | PASS
Email sent + message displayed
PP4 - Aneta's Glimmer
Test Case 008 - Commenting - Styles & News
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Login | Login form displayed | Worked as expected | PASS
3 | Provide correct credentials and click login button | My Bookings Page displayed | Worked as expected | PASS
4 | Navigate to News | News List displayed | Worked as expected | PASS
5 | Select one of the News posts | News details displayed | Worked as expected | PASS
6 | Click "Show comments" icon | Comment form and comments of others displayed | Worked as expected | PASS
7 | Fill in comment | None | Worked as expected | PASS
8 | Click "Comment" button | Message displayed | Worked as expected | PASS
News detail page realods
9 | Navigate to Styles | Styles List displayed | Worked as expected | PASS
10 | Select one of the Styles | Style details displayed | Worked as expected | PASS
11 | Click "Show comments" icon | Comment form and comments of others displayed | Worked as expected | PASS
12 | Fill in comment | None | Worked as expected | PASS
13 | Click "Comment" button | Message displayed | Worked as expected | PASS
News detail page realods
PP4 - Aneta's Glimmer
Test Case 009 - Liking News & Liking, Trying Styles
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Login | Login form displayed | Worked as expected | PASS
3 | Provide correct credentials and click login button | My Bookings Page displayed | Worked as expected | PASS
4 | Navigate to News | News List displayed | Worked as expected | PASS
5 | Select one of the News posts | News details displayed | Worked as expected | PASS
6 | Click "Like" icon | Message displayed | Worked as expected | PASS
7 | See Likes name | Your name displayed | Worked as expected | PASS
8 | Click Likes names | Modal with names displayed | Worked as expected | PASS
9 | Click "Back" button | Modal closes | Worked as expected | PASS
10 | Navigate to Styles | Styles List displayed | Worked as expected | PASS
11 | Select one of the Styles | Style details displayed | Worked as expected | PASS
12 | Click "Like" icon | Message displayed | Worked as expected | PASS
13 | Click Likes names | Modal with names displayed | Worked as expected | PASS
14 | Click "Back" button | Modal closes | Worked as expected | PASS
15 | Click "Try" icon | Message displayed | Worked as expected | PASS
16 | Click Try names | Modal with names displayed | Worked as expected | PASS
17 | Click "Back" button | Modal closes | Worked as expected | PASS
PP4 - Aneta's Glimmer
Test Case 010 - Deleting user account
Step # | Step Description | Expected Action | Actual Action | Result | Comment
1 | Navigate to Aneta's Glimmer Page | Landing Page Displayed | Worked as expected | PASS
2 | Click on Login | Login form displayed | Worked as expected | PASS
3 | Provide correct credentials and click login button | My Bookings Page displayed | Worked as expected | PASS
4 | Click on My Profile | Prepopulated My Profile Form displayed | Worked as expected | PASS
5 | Click "Delete Account" button | Modal displayed | Worked as expected | PASS
6 | Click "Back" button | Prepopulated My Profile Form displayed | Worked as expected | PASS
7 | Click "Delete Account" button | Modal displayed | Worked as expected | PASS
8 | Click "Delete my account" button | Landing Page Displayed | Worked as expected | PASS